## Main Board
Date | Designater | Before |  | Change Type | After |  | Reason | BOM Update | Schematic Update
|  | Value | TYM P/N |  | Value | TYM P/N
20190710 | C176 | 150pF X7R | T542021517508 | Change To | 150pF NPO | T541021516508 | Change to NPO for better PLL | YES | YES
| R290,R291,R292,R293,R294,R295,R296,R297,R298,R299,R300,R301,R302,R303,R304,R305,R306,R307,R308,R309,R310,R311,R312,R313 |  |  | Add | 0R 0603 | T5020000024A9 | Add add R 0603 for better PLL | YES | YES
| R117 | 1M 0603 | T502100402399 | Change To | 1M 0402 | T502100401399 | change to 0402 for better Layout | YES | YES
| R240 | 10K 0402 | T502100201399 | Change To | 0R 0603 | T502000002009 | Power control correction | YES | YES
| R239 | 3.9K 0402 | T502390101399 | Change To | 100K 0603 | T502100302399 | Power control correction | YES | YES
| L1,L2,L3,L4,L5,L6,L7 | 600R@100MHz | T710500029300 | Delete |  |  | Remove ferrite bead | YES | YES
| R314,R315,R316,R317,R318,R319,R320 |  |  | Add | 0R 0603 | T502000002009 | Replace by 0R resistor | YES | YES
| R280 | 10K 0603 | T502100202399 | Change To | 1K 0603 | T502100102399 | Optimize the 5V DC-DC circuit | YES | YES
| R271,R277 | 10K 0603 | T502100202399 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| C230 | 0.22uF 0603 | T542022247508 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| Q27 | DMP3099L-7 | T585002550438 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| R270 | 511K 0603 | T502511302399 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| R276 | 105K 0603 | T502105302399 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| R283 | 22K 0402 | T502220201399 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| Q28 | MMBT3904WT1G | T581004222440 | Delete |  |  | Optimize the 5V DC-DC circuit | YES | YES
| R238,R247 | 33R 0402 | T502330A01399 | Change To | 0R 0603 | T502000002009 | Change to 0603 for better routing | NO | YES
| R276,R277 |  |  | Add | 33R 0402 | T502330A01399 | Add dumping resistor | NO | YES
| J9 | 10 pin 1.5mm connector | T690300109200 | Change To | 22 pin FPC | T690300162900 | Design update for better assembly | NO | YES
| J10 | 11 pin 1.5mm connector | T690300109300 | Delete |  |  |  | NO | YES

## Power Amp Board
Date | Designater | Before |  | Change Type | After |  | Reason | BOM Update | Schematic Update
|  | Value | TYM P/N |  | Value | TYM P/N
20190703 | J2 | 28 Pin DIP | T690300165000 | Change To | 28 Pin SMT | T690300164900 | Change the DIP part to SMT, same as used on Main Board | YES | YES
| D4,D5 | AVRM1005C120MTAAB | T710500020400 | Delete |  |  | Move SMB control to Main board | YES | YES
| J3 | 2 Pin connector | T690300140400 | Delete |  |  | No need EQ detection connection | YES | YES
| J4 | 10 Pin 2.5 mm | T690300164100 | Change To | 5 pin DIP 3.96mm | T690300170000 | Optimize Battery power connection | YES | YES
| J6 | 4 Pin 90 deg C | T690300164300 | Change To | 4 Pin 180deg C | T690300129900 | For ME require | YES | YES
| J8 | 2 Pin 90 deg C | T690300164200 | Change To | 2 pin 180 deg C | T690300152100 | For ME require | YES | YES
| R269,R270,R271,R272,R273,R274,R275,R276,R277,R278,R279,R280,R281,R282,R283,R284,R285,R286,R287,R288,R289,R290,R291,R292 |  |  | Add | 0R 0603 | T5020000024A9 | For EMC option, add 24 pcs | YES | YES
| R129 | 8.2K OHM | T502820102399 | Change To | 6.2K OHM | T502620102399 |  | YES | YES
| R130,R131 | 100K OHM | T502100302399 | Change To | 10K OHM | T502100202399 |  | YES | YES
| R141,R142 | 10K OHM | T502100202399 | Change To | 1K OHM | T502100102399 |  | YES | YES
| R136 | 16.5K OHM | T502165202399 | Change To | 15K OHM | T502150202399 |  | YES | YES
| R116 | 20 OHM | T502200A02399 | Change To | 15 OHM | T502015002499 |  | YES | YES
| R113 | 0R 0805 | T502000003009 | Change To | 100R 0805 | T502100003399 |  | YES | YES
| R132 | 1K OHM | T502100102399 | Change To | 2K OHM | T502200102399 |  | YES | YES
| R134 | 33K OHM | T502330202399 | Change To | 15K OHM | T502150202399 |  | YES | YES
| R133 | 3.3K OHM | T502330102399 | Delete |  |  |  | YES | YES
| D29 | 1N4148WS | T572005070208 | Delete |  |  |  | YES | YES
| D47 | BAV99 | T572003550122 | Delete |  |  |  | YES | YES
| C112 | 0.1uF | T542021047605 | Delete |  |  |  | YES | YES
| C45 | 1uF | T542031057408 | Delete |  |  |  | YES | YES

## Volume Board
Date | Designater | Before |  | Change Type | After |  | Reason | BOM Update | Schematic Update
|  | Value | TYM P/N |  | Value | TYM P/N
20190716 | VR1,VR2 | C10KX2 | T531230000320 | Change To | C10KX2 | T531230000420 | P/N change | YES | NO